## Sheet1
Proposed Technology for Marketplace
Technology : Ionic 4 for Front End + Angular 5 for Backend.
API : Codeignitor
Database : MySQL
Android/iOS + Web : ionic 4 base will be used internally
Realtime Chatting : Firebase
Upper Level Development Scope | Timeline | Comments | Upper Level Development Scope | Comments
Website UI + HTML Generation for Website | 2 Months | - Icon Desigining - Theme Designing - Logo Designing - Content - Website Flow - CSS HTML using Ionic Framework for Website - Mobile App Icon design (compatible for iOS and Android) - Button Icon for Mobile App | Website UI + HTML Generation for Website | - Content - Website Flow - CSS HTML using Ionic Framework for Website
Services/API | 2 Months | - Database Designing - Database Integration with Services - API development for all relevant functionalities that will be used throughout Website and Mobile Apps | Services/API | - Database Designing - Database Integration with Services - API development for all relevant functionalities that will be used throughout Website
Core Website Development | 4 Month | - User Generation - User Management [Login/Security/Password Reset/FB and Google Integration] - Project Management Cycle [Adding/Removing Project, Project Approval, Proejct Bidding Process, Project Finance Management based on Project Type] - Time Tracking implementation - Payment Management [Escrow Handling, Payment Gateway Integration, Payment Tracking against Project, Commision Deduction, Penelties - Real time chatting interfacing using Firebase Api - Push Notifications to user throughout website [SMS / Emailing] | Core Website Development | - User Generation - User Management [Login/Security/Password Reset/FB and Google Integration] - Project Management Cycle [Adding/Removing Project, Project Approval, Proejct Bidding Process, Project Finance Management based on Project Type] - Time Tracking implementation - Payment Management [Escrow Handling, Payment Gateway Integration, Payment Tracking against Project, Commision Deduction, Penelties - Real time chatting interfacing using Firebase Api - Push Notifications to user throughout website [SMS / Emailing]
CMS Development [For Adminsitrator Role] | 1 Month | - Page Management - User Management - User Rights Management - Templates Emailing/Sms Management - SEO Management - Financial Management for Accounts/Payments/Escrow | CMS Development [For Adminsitrator Role] | - Page Management - User Management - User Rights Management - Templates Emailing/Sms Management - SEO Management - Financial Management for Accounts/Payments/Escrow
Ios/Android App Generation | 3 Week | ionic controls within core website will be build in iOS and Android applications reducing App Development Cost | Envrioment Setup
Envrioment Setup / Amazon Servers Hardening and Setup | 1 Week |  | Beta Testing / Bug Fixing | Post deployment, testing will be carried out and fault fixing will be done throughout untill signoff
Beta Testing / Bug Fixing | 1 Month | Post deployment, testing will be carried out and fault fixing will be done throughout untill signoff